## Total Efforts
High Level Project Features, Milestones And Cost Estimations
Project Name: Online Video Commenting System Web Portal Project Id: MAYNARD02
Features / Tasks | Estimated Hours | Estimated Cost (₹)
REQUIREMENT ANALYSIS AND SYSTEM DESIGN
Design and user Interface | 16 | 6400 | Click to see Break Up
Web site development Admin | 0 | 0 | Click to see Break Up
Frong End User Development | 177 | 70800 | Click to see Break Up
Cost of Application
Working Hours (Duration) | 193 | 77200 |  | 9650 | 1930
Delivery Schedule (Tentative) |  | Within 50 Working Days
Few Highlights
• Proposal only valid for 20 days
• 25% Upfront Payment Required
• 60 days bug fixing and support available without additional cost
• Staging server provided for interim and fast paced delivery
• Source code protected under NDA & IPR
• Infrastructure available with 99.99% uptime & 100% power backup available
• Team and/or Point of contact available in your working hours (as per the project need)

## DESIGN (Wireframes, UI)
S.NO | Tasks | Estimate Hours | Back
1 | Application Graphics Creation 1) Home Page 2) Search 3) Login 4) Forgot Password 5) Contact Screen 6) Company Screen 7) Task List Screen 8) Company Network Map 9) Report UI | 16
TOTAL |  | 16

## Admin
S.NO | Tasks | Estimate Hours | Back
1 | N/A | 0
2 | N/A | 0
3 | N/A | 0
TOTAL |  | 0

## FrontEndUsers
S.NO | Tasks | Estimate Hours | Back
1 | Home page Dynamic | 8
2 | Contact Management | 16
3 | Company Management | 16
4 | Team Management | 16
5 | Opporturnity Management | 24
6 | Task Management | 32
7 | Company Network Work Management | 24
8 | Report | 16
14 | Dataparsing implementation | 9
15 | Testing | 16
TOTAL |  | 177